## Sheet1
Tasks | Hours
Task 1 Week 1
Set up a Git Repo | 10 min
Set up Trello for each task | 20 min
Create a sample WPF program | 30 min
Follow online resoure for tips | 10 min
Task 2 Week 1
Create the methods for URI conn. | 5 hrs
Figure out how to use oauth 2.0 | 5 hrs
Connect parser and library to sample console | 3 hrs
Fix bugs that shown up | 3 hrs
Task 3 : Week 2
Connect parser and library to WPF | 5 hrs
Properly implement library | 5 hrs
Fix bugs in the from connecting library and WPf | 10 hrs
Task 4: Week 3
Write up documentation | 1 hr
Write up log for testers | 1 hr
Find up to 10 students to test app | 1 hr
Keep a log of suggestions | 1 hr
Listen to feedback and make necessary changes | 10 hr
Task 5: Week 4
Create Icons for notification | 1 . 45 hr
Make sure application runs from taskbar | 6 hrs
Test notifications | 3 hrs
Make necessary changes to UI | 6 hrs
Task 6 : Week 5
Keep a log of suggestions | 3 hrs
Listen to feedback and make necessary changes | 5 hrs
Task 7 : Week 6
Research proxy / alert system | 19 hrs
Set up a alert program | 3 hrs
Set a timer for alert system | 3 hrs
Task 8: Week 7
Keep a log of suggestions | 3 hrs
Listen to feedback and make necessary changes | 3hrs
Decide where to place DistractionRemover | 5hrs
Task 9: Week 8
Update UI for users | 16hrs
Clean up code | 8 hrs
Try to implement stretch goals | 3 hrs
Fix persistant bugs | 3 hrs